## Sheet1
Defect ID | Submitted Date | Issue Description | Sprint Detected In | Assigned Engineer | Issue Type | Corrective Action | Action Taken Date | Defect Status | Notes
1 | 2025-11-27 | OCR output not extracting full address from Aadhaar image | Sprint 1 | Backend Team | Functional | Improved preprocessing and added Tesseract config for multi-line extraction | 2025-12-14 | Closed | Verified successfully
2 | 2025-12-15 | Model output returning inconsistent address verification scores | Sprint 2 | Backend Team | Algorithmic | Adjusted threshold values and retrained model | 2025-12-17 | Closed | Performance improved
3 | 2025-12-18 | Frontend not displaying fraud prediction results correctly | Sprint 2 | Frontend Team | UI/Integration | Fixed JSON parsing and updated API endpoint in React | 2025-12-20 | Closed | Tested and verified
4 | 2025-12-21 | GNN model showing NaN values during training | Sprint 2 | Backend Team | Model Training | Normalized data and fixed null entries in graph edges | 2025-12-22 | Closed | Stable model output
5 | 2025-12-24 | AML check module failing on duplicate address input | Sprint 3 | Backend Team | Logic | Added address hashing and duplicate detection rule | 2025-12-27 | Closed | Verified via testing
6 | 2025-12-29 | Upload form not handling invalid file formats | Sprint 3 | Frontend Team | UI/Validation | Added MIME type check and error popup | 2025-12-31 | Closed | User-friendly validation added
7 | 2026-01-04 | Real-time pipeline response delay | Sprint 3 | Backend Team | Performance | Implemented async processing and caching | 2026-01-08 | Closed | Latency reduced by 35%
8 | 2026-01-10 | Dashboard graphs not updating after backend changes | Sprint 4 | Frontend Team | Integration | Re-linked data binding with new API route | 2026-01-14 | Closed | Graph sync issue resolved
9 | 2026-01-16 | Fraud alerts not showing in admin view | Sprint 4 | Backend Team | Functional | Fixed alert trigger logic in API | 2026-01-19 | Closed | Verified
10 | 2026-01-20 | Minor typo and alignment issues in UI | Sprint 4 | Frontend Team | UI | Adjusted CSS layout and corrected labels | 2026-01-22 | Closed | Presentation-ready