## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a Data Engineer, I want to collect real-world enterprise email datasets so that the system can be trained on realistic data | Must Have | Project kickoff | Data Engineer | Completed
Sprint 1 | Sprint 1 | US-02 | As an ML Engineer, I want to clean raw email text so that noise does not affect model performance | Must Have | US-01 | ML Engineer | Completed
Sprint 1 | Sprint 1 | US-03 | As a Data Scientist, I want to preprocess cleaned emails so that they are ready for ML workflows | Must Have | US-02 | Data Scientist | Completed
Sprint 1 | Sprint 1 | US-04 | As an ML Engineer, I want to encode category and urgency labels so that models can learn effectively | Should Have | US-03 | ML Engineer | Completed
Sprint 1 | Sprint 1 | US-05 | As an ML Engineer, I want to convert email text into numerical features so that ML models can process it | Must Have | US-04 | ML Engineer | Completed
Sprint 1 | Sprint 1 | US-06 | As a Data Scientist, I want to split the dataset so that model performance can be evaluated | Should Have | US-05 | Data Scientist | Completed
Sprint 2 | Sprint 2 | US-07 | As an ML Engineer, I want a baseline classifier for email categories so that benchmarks are established | Must Have | US-06 | ML Engineer | Completed
Sprint 2 | Sprint 2 | US-08 | As an ML Engineer, I want a lightweight classifier so that predictions are fast | Should Have | US-07 | ML Engineer | Completed
Sprint 2 | Sprint 2 | US-09 | As an AI Engineer, I want to improve accuracy using transformers so that predictions are more accurate | Must Have | US-07 | AI Engineer | In Progress
Sprint 2 | Sprint 3 | US-10 | As an AI Engineer, I want efficient transformer-based classification so that performance is optimized | Could Have | US-09 | AI Engineer | To Do
Sprint 2 | Sprint 3 | US-11 | As a Data Scientist, I want to compare all trained models so that the best one is selected | Must Have | US-08, US-09 | Data Scientist | To Do
Sprint 3 | Sprint 3 | US-12 | As a Support Manager, I want urgent emails detected immediately so that issues are prioritized | Must Have | US-07 | Product Owner | Completed
Sprint 3 | Sprint 3 | US-13 | As an ML Engineer, I want urgency detected using ML so that prioritization is automated | Must Have | US-12 | ML Engineer | In Progress
Sprint 3 | Sprint 3 | US-14 | As a System Designer, I want rule-based urgency to override ML predictions when critical | Must Have | US-13 | System Designer | To Do
Sprint 3 | Sprint 3 | US-15 | As an ML Engineer, I want to integrate and validate urgency prediction results so that the system reliably identifies critical emails | Must Have | US-13, US-14 | ML Engineer | To Do

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 5.5 | 5.5 | 4 | 5 | 7 | 5 | 7 | 7 | 3 | 4.5 | 2 | 2 | 1.5 | 1.5
SPRINT 1 BACKLOG
US 01 | T 01 | Identify public & enterprise email datasets | 2025-11-27 | 11/28/2025 | Data Engineer | Analysis | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | T 02 | Download and validate email datasets | 11/29/2025 | 11/30/2025 | Data Engineer | Data Collection | Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 02 | T 03 | Remove headers, HTML tags, signatures | 2025-12-01 | 2025-12-02 | ML Team | Data Cleaning | Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 02 | T 04 | Normalize text (lowercase, punctuation) | 2025-12-03 | 2025-12-04 | ML Team | Preprocessing | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 03 | T 05 | Tokenization & stopword removal | 2025-12-05 | 2025-12-06 | Data Scientist | Preprocessing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 03 | T 06 | Lemmatization & text finalization | 2025-12-07 | 2025-12-08 | Data Scientist | Preprocessing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 04 | T 07 | Encode category labels | 2025-12-07 | 2025-12-09 | ML Team | Feature Engineering | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
US 04 | T 08 | Encode urgency labels | 2025-12-11 | 2025-12-12 | ML Team | Feature Engineering | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US 05 | T 09 | Generate TF-IDF vectors | 2025-12-12 | 2025-12-13 | ML Team | Feature Engineering | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 06 | T 10 | Train-test data split | 2025-12-13 | 2025-12-14 | Data Scientist | Validation | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US 07 | T 11 | Prepare training pipeline | 2025-12-14 | 2025-12-15 | ML Team | Setup | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 07 | T 12 | Train Logistic Regression | 2025-12-15 | 2025-12-16 | ML Team | Training | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 08 | T 13 | Train Naive Bayes | 2025-12-16 | 2025-12-17 | ML Team | Training | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 08 | T 14 | Evaluate NB model | 2025-12-17 | 2025-12-18 | ML Team | Evaluation | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 09 | T 15 | Prepare data for BERT | 2025-12-18 | 2025-12-19 | AI Team | Data prep | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 09 | T 16 | Fine-tune BERT | 2025-12-19 | 2025-12-20 | AI Team | Training | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 10 | T 17 | Implement DistilBERT | 2025-12-20 | 2025-12-21 | ML Team | Training | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 11 | T 18 | Compare all models | 2025-12-21 | 2025-12-22 | Backend Team | Model Training | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US 12 | T 19 | Define urgency needs | 2025-12-22 | 2025-12-23 | ML Team | Model Training | Completed | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 12 | T 20 | Identify urgency indicators | 2025-12-23 | 2025-12-24 | QA Team | Transformer Training | Completed | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 13 | T 21 | Train urgency classifier | 2025-12-24 | 2025-12-26 | ML Team | Training | Completed | 5 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 14 | T 22 | Define urgency rules | 2025-12-28 | 2025-12-27 | ML Team | Urgency Rules | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US 14 | T 23 | Implement override logic | 2025-12-29 | 2025-12-30 | QA Team | Implementation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
US 15 | T 24 | Integrate ML & rules | 2025-12-31 | 2026-01-04 | ML Team | Urgency ML | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 2 | 0 | 0
US 15 | T 25 | Validate urgency results | 2026-01-05 | 2026-01-08 | Backend Team | Hybrid Logic | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5
SPRINT 4 BACKLOG
US 16 | T 26 | Design dashboard layout & components | 2026-01-09 | 2026-01-10 | Frontend Team | Design | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 16 | T 27 | Implement dashboard UI | 2026-01-11 | 2026-01-12 | Frontend Team | Development | In progress | 5 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 17 | T 28 | Implement category & urgency filters | 2026-01-12 | 2026-01-14 | Frontend Team | Development | To Do | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 17 | T 29 | Add analytics charts | 2026-01-15 | 2026-01-16 | Data Scientist | Visualization | To Do | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 18 | T 30 | Develop REST API for classification | 2026-01-16 | 2026-01-17 | Backend Team | Development | To Do | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US 18 | T 31 | Integrate dashboard with backend APIs | 2026-01-18 | 2026-01-19 | Full Stack Dev | Integration | To Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0
US 19 | T 32 | Deploy application to cloud | 2026-01-19 | 2026-01-20 | DevOps Team | Deployment | To Do | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
US 19 | T 33 | Perform final system validation | 2026-01-21 | 2026-01-22 | QA Team | Testing | To Do | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Raw emails contained HTML and noise | Applied HTML and regex-based cleaning
Sprint 1 | Day 2 | Missing values in email dataset | Removed null records and validated data
Sprint 1 | Day 3 | Large dataset slowing preprocessing | Optimized preprocessing pipeline
Sprint 1 | Day 4 | Label inconsistencies | Standardized category labels
Sprint 1 | Day 5 | Imbalanced data distribution | Reviewed dataset composition
Sprint 2 | Day 1 | Baseline model accuracy was low | Tuned TF-IDF parameters
Sprint 2 | Day 2 | Naive Bayes overfitting | Adjusted feature size
Sprint 2 | Day 3 | Transformer training very slow | Reduced batch size
Sprint 2 | Day 4 | High memory usage during training | Used DistilBERT instead of BERT
Sprint 2 | Day 5 | Evaluation metrics inconsistent | Used macro F1 for comparison
Sprint 3 | Day 1 | ML urgency missed critical emails | Introduced rule-based urgency
Sprint 3 | Day 2 | False positives in urgency detection | Refined urgency keywords
Sprint 3 | Day 3 | Conflict between ML and rules | Implemented hybrid override logic
Sprint 3 | Day 4 | Testing hybrid logic | Validated with sample emails
Sprint 3 | Day 5 | Final validation pending | Completed end-to-end testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-27 | 2025-12-11 | Data Engineer | Automate cleaning scripts | Manual cleaning steps | Using regex-based preprocessing | Standardized preprocessing pipeline
2 | Sprint 2 | 2025-12-12 | 2025-12-25 | ML Engineer | Hyperparameter tuning | Training without evaluation | Baseline + transformer comparison | Selected best-performing models
3 | Sprint 3 | 2025-12-26 | 2026-01-08 | AI Engineer | Hybrid urgency logic | Pure ML urgency detection | Rule-based overrides | Improved urgency precision
4
5
6
7